## Stories
Sprint | Story | Estimate
1 | 2013-04-11
| Story #1 | 1
| Story #2 | 3
| Story #3 | 5
2 | 2013-04-25 |  | 9
| Story #4 | 5
| Story #5 | 3
| Story #6 | 5
3 | 2013-05-09 |  | 13
| Story #7 | 3
| Story #8 | 3
| Story #9 | 5
4 | 2013-05-23 |  | 11
| Story #10 | 3
| Story #11 | 3
| Story #12 | 5
5 | 2013-06-06 |  | 11
| Story #13 | 1
| Story #14 | 3
| Story #15 | 5
Release June 1
| Total | 53
| Completed | 44
| Remaining | 9
| % Complete | 83.02%
| Avg Velocity | 11
| Estimated # Iterations Remaining | 0.81818
Parking Lot
| Nice to have story #1 | 3
| Nice to have story #2 | 5
Dropped
| Stuff we didn't need #1 | 6
Stuff we didn't need #2

## Sprint Data
| 2013-04-11 | 2013-04-25 | 2013-05-09 | 2013-05-23
| 1 | 2 | 3 | 4
Total Effort | 53 | 53 | 53 | 53
Velocity | 9 | 13 | 11 | 11
Remaining | 44 | 31 | 20 | 9
Completed | 9 | 22 | 33 | 44
% complete | 16.98% | 41.51% | 62.26% | 83.02%