## Table Of Contents
Table Of Contents
Table Of Contents
Dashboard
RAG Status
Project Manager Status
Task Counts
Tables
Schedule
Raw Schedule
File Info

## Dashboard
Last Update 07-06-2022 |  | Return to the table of contents
Total Status Light--> | 68.24% | Key Status Light Value--> | 68.97% | Critical Path Status Light--> | 66.67% | Set Value Ranges
[6 empty] | Min | Max
red | 1 | red | 1 | red | 1 | 41% | 100%
orange | #N/A | orange | #N/A | orange | #N/A | 30% | 40%
green | #N/A | green | #N/A | green | #N/A | 0% | 30%
| Status | Percentage
Red | 58 | 68.2353
Amber | #REF! | #REF!
Green | 27 | 31.7647

## RAG Status
Last Update 07-06-2022 | Return to the table of contents
|  | Total Status Light--> | 68.24% | Key Status Light Value--> | 68.97% | Critical Path Status Light--> | 66.67% | Set Value Ranges
[8 empty] | Min | Max
|  |  | 1 | red | 1 |  | 1 | 41% | 100%
|  |  | #N/A | orange | #N/A |  | #N/A | 30% | 40%
|  |  | #N/A | green | #N/A |  | #N/A | 0% | 30%

## Project Manager Status
Last Update 07-06-2022 | Return to the table of contents

## Task Counts
Last Update 07-06-2022 | Return to the table of contents

## Tables
Last Update 07-06-2022 |  | Return to the table of contents
Hub by Status |  |  |  | Key Milestone Count |  |  | Key Milestone by PM |  |  |  | Row Labels | Count of Hub +
Quanty |  |  |  | Key | Quantity |  | Key Deliverable + | (All) |  |  | Go Live | 19
Hub | Red | Green | Total | Yes | 58 | [5 empty] | Implementation | 30
Go Live | 11 | 4 | 15 | No | 27 |  | Count of RAG + | Column Labels |  |  | Planning | 63
Implementation | 18 | 9 | 27 | Total | 85 |  | PM | Red | Green | Total | Grand Total | 112
Planning | 29 | 14 | 43 |  |  |  | Bob | 34 | 12 | 46
Total | 58 | 27 | 85 | Key Deliverable + | Yes |  | Jeff | 14 | 11 | 25 | Row Labels | Count of Work Stream +
[7 empty] | Sam | 10 | 4 | 14 | Band | 16
|  |  |  | Status | Quantity | Percentage | Total | 58 | 27 | 85 | Creative | 3
Work Stream by Status |  |  |  | Red | 40 | 68.97% |  |  |  |  | Finance and Accounting | 12
Quantity |  |  |  | Green | 18 | 31.03% | Key Deliverable + | Yes |  |  | Human Resources | 6
Work Stream | Red | Green | Total | Total | 58 | 100% |  |  |  |  | Logistics | 9
Band | 12 | 4 | 16 |  |  |  | Count of RAG Staus |  |  |  | Manager | 18
Creative | 2 | 1 | 3 |  |  |  | PM | Red | Green | Total | PR | 9
Finance and Accounting | 8 | 4 | 12 | Key Deliverable + | No |  | Bob | 26 | 9 | 35 | PR/Band | 3
Human Resources | 4 | 2 | 6 |  |  |  | Jeff | 9 | 7 | 16 | Travel | 6
Logistics | 6 | 3 | 9 | Status | Quantity | Percentage | Sam | 5 | 2 | 7 | Vendor | 3
Manager | 12 | 6 | 18 | Red | 18 | 66.67% | Total | 40 | 18 | 58 | Grand Total | 85
PR | 6 | 3 | 9 | Green | 9 | 33.33%
PR/Band | 2 | 1 | 3 | Total | 27 | 100% | Key Deliverable + | No
Travel | 4 | 2 | 6
Vendor | 2 | 1 | 3 |  |  |  | Count of RAG Staus
Total | 58 | 27 | 85 | Key Deliverable + | (All) |  | PM | Red | Green | Total
[7 empty] | Bob | 8 | 3 | 11
Critical Path | Yes |  |  | Status | Quantity | Percentage | Jeff | 5 | 4 | 9
|  |  |  | Red | 58 | 68.24% | Sam | 5 | 2 | 7
Row Labels | Count of Critical | Percentage |  | Green | 27 | 31.76% | Total | 18 | 9 | 27
Red | 2 | 66.67% |  | Total | 85 | 100%
Green | 1 | 33.33%
Grand Total | 3 | 100%

## Schedule
Last Update 07-06-2022 |  | Return to the table of contents
Critical | Summary | Task ID * | % Complete | Days Until Start + | Days Until Finish + | Days Since Completed + | Hub + | Work Stream + | Project Manager * | Task Name | Start | Finish | Actual Start | Actual Finish | Duration | Key Deliverable + | Predecessors | Active | RAG + | RAG Staus
No | No | 9 | 1 | -369 | -268 | 268 | Planning | Creative | Sam | Promotional Artwork | 2021-02-08 | 2021-06-25 | 2021-02-08 | 2021-06-25 | 101 | No | 37FS-120 days | Yes | -369 | Red
No | No | 44 | 1 | -314 | -288 | 288 | Planning | Manager | Sam | Design Approvals | 2021-04-26 | 2021-05-28 | 2021-04-26 | 2021-05-28 | 26 | Yes | 22 | Yes | -314 | Red
No | No | 43 | 1 | -369 | -314 | 314 | Planning | Vendor | Sam | Proof Design | 2021-02-08 | 2021-04-23 | 2021-02-08 | 2021-04-23 | 55 | No | 37FS-120 days | Yes | -369 | Red
No | No | 46 | 0 | -418 | -133 |  | Implementation | Finance and Accounting | Jeff | Payroll | 2020-12-01 | 2021-12-31 |  |  | 285 | Yes |  | Yes | -418 | Red
No | No | 45 | 0 | -418 | -133 |  | Implementation | Finance and Accounting | Jeff | Taxes | 2020-12-01 | 2021-12-31 |  |  | 285 | Yes |  | Yes | -418 | Red
No | No | 48 | 0 | -418 | -133 |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 2020-12-01 | 2021-12-31 |  |  | 285 | No |  | Yes | -418 | Red
No | No | 47 | 0 | -418 | -133 |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 2020-12-01 | 2021-12-31 |  |  | 285 | No |  | Yes | -418 | Red
No | No | 39 | 1 | -369 | -339 | 339 | Planning | Human Resources | Bob | Hiring | 2021-02-08 | 2021-03-19 | 2021-02-08 | 2021-03-19 | 30 | Yes | 37FS-120 days | Yes | -369 | Red
No | No | 38 | 1 | -369 | -339 | 339 | Planning | Human Resources | Bob | Training | 2021-02-08 | 2021-03-19 | 2021-02-08 | 2021-03-19 | 30 | No | 37FS-120 days | Yes | -369 | Red
No | No | 41 | 1 | -369 | -279 | 279 | Planning | Logistics | Sam | Rentals | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -369 | Red
No | No | 42 | 1 | -369 | -279 | 279 | Planning | Logistics | Sam | Purchasing | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -369 | Red
No | No | 40 | 1 | -369 | -339 | 339 | Planning | Logistics | Sam | Shipping - Venue to Venue | 2021-02-08 | 2021-03-19 | 2021-02-08 | 2021-03-19 | 30 | Yes | 37FS-120 days | Yes | -369 | Red
No | No | 36 | 1 | -369 | -279 | 279 | Planning | Manager | Bob | Contracts | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -369 | Red
No | No | 37 | 1 | -369 | -279 | 279 | Planning | Manager | Bob | Ryders | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -369 | Red
No | No | 33 | 1 | -336 | -276 | 276 | Planning | Manager | Bob | Vehice Leasing | 2021-03-25 | 2021-06-15 | 2021-03-25 | 2021-06-15 | 60 | No | 37FS-120 edays | Yes | -336 | Red
No | No | 35 | 1 | -336 | -306 | 306 | Planning | Manager | Bob | Licensing and Insurance | 2021-03-25 | 2021-05-04 | 2021-03-25 | 2021-05-04 | 30 | No | 37FS-120 edays | Yes | -336 | Red
No | No | 32 | 0.5 | -367 | -337 |  | Planning | Travel | Jeff | Hotels | 2021-02-10 | 2021-03-23 | 2021-02-10 |  | 30 | Yes | 37FS-120 days | Yes | -367 | Red
No | No | 31 | 1 | -367 | -337 | 337 | Planning | Travel | Jeff | Transportation | 2021-02-10 | 2021-03-23 | 2021-02-10 | 2021-03-23 | 30 | Yes | 37FS-120 days | Yes | -367 | Red
Yes | No | 49 | 0 | -418 | -264 |  | Planning | Band | Bob | Rehearsals | 2020-12-01 | 2021-07-01 |  |  | 154 | Yes | 37FS-240 days | Yes | -418 | Red
No | No | 50 | 0 | -309 | -159 |  | Implementation | Manager | Bob | Ticket Sales | 2021-05-01 | 2021-11-25 |  |  | 150 | Yes |  | Yes | -309 | Red
No | No | 51 | 0 | -418 | -264 |  | Implementation | PR | Bob | Promotional events | 2020-12-01 | 2021-07-01 |  |  | 154 | Yes |  | Yes | -418 | Red
No | No | 56 | 0 | -395 | -159 |  | Implementation | PR | Bob | Radio advertising buys | 2021-01-01 | 2021-11-25 |  |  | 236 | No |  | Yes | -395 | Red
No | No | 55 | 0 | -395 | -159 |  | Implementation | PR | Bob | TV advertising buys | 2021-01-01 | 2021-11-25 |  |  | 236 | No |  | Yes | -395 | Red
No | No | 54 | 0 | -418 | -159 |  | Implementation | PR/Band | Bob | Promotional Interviews | 2020-12-01 | 2021-11-25 |  |  | 259 | Yes |  | Yes | -418 | Red
Yes | No | 20 | 0 | -264 | -249 |  | Go Live | Band | Bob | New York, NY | 2021-07-02 | 2021-07-22 |  |  | 15 | Yes |  | Yes | -264 | Red
No | No | 19 | 0 | -247 | -227 |  | Go Live | Band | Bob | Philadelphia, PA | 2021-07-27 | 2021-08-23 |  |  | 20 | Yes | 37FS+2 days | Yes | -247 | Red
No | No | 18 | 0 | -225 | -201 |  | Go Live | Band | Bob | Washington, DC | 2021-08-26 | 2021-09-28 |  |  | 24 | Yes | 38FS+2 days | Yes | -225 | Red
No | No | 17 | 0 | -199 | -189 |  | Go Live | Band | Bob | New Orleans, LA | 2021-10-01 | 2021-10-14 |  |  | 10 | Yes | 39FS+2 days | Yes | -199 | Red
No | No | 22 | 0 | -184 | -174 |  | Go Live | Band | Bob | Austin, TX | 2021-10-22 | 2021-11-04 |  |  | 10 | Yes | 40FS+5 days | Yes | -184 | Red
No | No | 21 | 0 | -169 | -159 |  | Go Live | Band | Bob | Los Angeles, CA | 2021-11-12 | 2021-11-25 |  |  | 10 | Yes | 41FS+5 days | Yes | -169 | Red
No | No | 108 | 0 | -200 | -110 |  | Planning | Creative | Jeff | Promotional Artwork | 2021-09-30 | 2022-02-02 |  |  | 90 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 110 | 0 | -200 | -186 |  | Planning | Manager | Bob | Design Approvals | 2021-09-30 | 2021-10-19 |  |  | 14 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 109 | 0 | -200 | -170 |  | Planning | Vendor | Sam | Proof Design | 2021-09-30 | 2021-11-10 |  |  | 30 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 112 | 0 | -156 | 127 |  | Implementation | Finance and Accounting | Jeff | Payroll | 2021-12-01 | 2022-12-31 |  |  | 283 | Yes |  | Yes | -156 | Red
No | No | 113 | 0 | -156 | 127 |  | Implementation | Finance and Accounting | Jeff | Taxes | 2021-12-01 | 2022-12-31 |  |  | 283 | Yes |  | Yes | -156 | Red
No | No | 114 | 0 | -156 | 127 |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 2021-12-01 | 2022-12-31 |  |  | 283 | No |  | Yes | -156 | Red
No | No | 115 | 0 | -156 | 127 |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 2021-12-01 | 2022-12-31 |  |  | 283 | No |  | Yes | -156 | Red
No | No | 101 | 0 | -200 | -170 |  | Planning | Human Resources | Bob | Hiring | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 102 | 0 | -200 | -170 |  | Planning | Human Resources | Bob | Training | 2021-09-30 | 2021-11-10 |  |  | 30 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 104 | 0 | -200 | -110 |  | Planning | Logistics | Bob | Rentals | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 105 | 0 | -200 | -110 |  | Planning | Logistics | Bob | Purchasing | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 106 | 0 | -200 | -170 |  | Planning | Logistics | Bob | Shipping - Venue to Venue | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 95 | 0 | -200 | -110 |  | Planning | Manager | Bob | Contracts | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 96 | 0 | -200 | -110 |  | Planning | Manager | Bob | Ryders | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 98 | 0 | -200 | -140 |  | Planning | Manager | Bob | Vehice Leasing | 2021-09-30 | 2021-12-22 |  |  | 60 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 99 | 0 | -200 | -170 |  | Planning | Manager | Bob | Licensing and Insurance | 2021-09-30 | 2021-11-10 |  |  | 30 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 92 | 0 | -200 | -170 |  | Planning | Travel | Jeff | Hotels | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 93 | 0 | -200 | -170 |  | Planning | Travel | Jeff | Transportation | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 135 | 0 | -178 | 99 |  | Implementation | Manager | Jeff | Ticket Sales | 2021-11-01 | 2022-11-22 |  |  | 277 | Yes | 78FS-90 edays | Yes | -178 | Red
No | No | 136 | 0 | -200 | -46 |  | Implementation | PR | Sam | Promotional events | 2021-09-30 | 2022-05-03 |  |  | 154 | Yes | 78FS-120 edays | Yes | -200 | Red
No | No | 137 | 0 | -200 | 36 |  | Implementation | PR | Sam | Radio advertising buys | 2021-09-30 | 2022-08-25 |  |  | 236 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 138 | 0 | -200 | 36 |  | Implementation | PR | Sam | TV advertising buys | 2021-09-30 | 2022-08-25 |  |  | 236 | No | 78FS-120 edays | Yes | -200 | Red
No | No | 139 | 0 | -122 | 155 |  | Implementation | PR/Band | Bob | Promotional Interviews | 2022-01-18 | 2023-02-08 |  |  | 277 | Yes | 78FS-10 edays | Yes | -122 | Red
No | No | 147 | 0 | -124 | -114 |  | Go Live | Band | Bob | Vancouver, BC | 2022-01-14 | 2022-01-27 |  |  | 10 | Yes |  | Yes | -124 | Red
No | No | 148 | 0 | -93 | -81 |  | Go Live | Band | Bob | Ottawa, ON | 2022-02-28 | 2022-03-15 |  |  | 12 | Yes | 78FS+30 edays | Yes | -93 | Red
No | No | 149 | 0 | -59 | -49 |  | Go Live | Band | Bob | Perth, ON | 2022-04-15 | 2022-04-28 |  |  | 10 | Yes | 79FS+30 edays | Yes | -59 | Red
No | No | 150 | 0 | -28 | -13 |  | Go Live | Band | Bob | Montreal, QB | 2022-05-30 | 2022-06-17 |  |  | 15 | Yes | 80FS+30 edays | Yes | -28 | Red
No | No | 151 | 0 | -3 | 12 |  | Go Live | Band | Bob | Quebec, QB | 2022-07-04 | 2022-07-22 |  |  | 15 | Yes | 81FS+15 edays | Yes | -3 | Red
No | No | 177 | 0 | 67 | 157 |  | Planning | Creative | Sam | Promotional Artwork | 2022-10-10 | 2023-02-10 |  |  | 90 | No | 118FS-120 edays | Yes | 67 | Green
No | No | 179 | 0 | 67 | 81 |  | Planning | Manager | Bob | Design Approvals | 2022-10-10 | 2022-10-27 |  |  | 14 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 178 | 0 | 67 | 97 |  | Planning | Vendor | Jeff | Proof Design | 2022-10-10 | 2022-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | 67 | Green
Yes | No | 181 | 0 | 312 | 594 |  | Implementation | Finance and Accounting | Bob | Payroll | 2023-09-18 | 2024-10-15 |  |  | 282 | Yes | 121FS+30 edays | Yes | 312 | Green
No | No | 182 | 0 | 105 | 387 |  | Implementation | Finance and Accounting | Jeff | Taxes | 2022-12-01 | 2023-12-31 |  |  | 282 | Yes |  | Yes | 105 | Green
No | No | 183 | 0 | 105 | 387 |  | Implementation | Finance and Accounting | Sam | Accounts recivable | 2022-12-01 | 2023-12-31 |  |  | 282 | No |  | Yes | 105 | Green
No | No | 184 | 0 | 105 | 387 |  | Implementation | Finance and Accounting | Bob | Accounts Payable | 2022-12-01 | 2023-12-31 |  |  | 282 | No |  | Yes | 105 | Green
No | No | 170 | 0 | 67 | 97 |  | Planning | Human Resources | Sam | Hiring | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 171 | 0 | 67 | 97 |  | Planning | Human Resources | Bob | Training | 2022-10-10 | 2022-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | 67 | Green
No | No | 173 | 0 | 67 | 157 |  | Planning | Logistics | Sam | Rentals | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 174 | 0 | 67 | 157 |  | Planning | Logistics | Bob | Purchasing | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 175 | 0 | 67 | 97 |  | Planning | Logistics | Jeff | Shipping - Venue to Venue | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 164 | 0 | 67 | 157 |  | Planning | Manager | Bob | Contracts | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 165 | 0 | 67 | 157 |  | Planning | Manager | Jeff | Ryders | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 167 | 0 | 67 | 127 |  | Planning | Manager | Bob | Vehice Leasing | 2022-10-10 | 2022-12-30 |  |  | 60 | No | 118FS-120 edays | Yes | 67 | Green
No | No | 168 | 0 | 67 | 97 |  | Planning | Manager | Jeff | Licensing and Insurance | 2022-10-10 | 2022-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | 67 | Green
No | No | 161 | 0 | 67 | 97 |  | Planning | Travel | Bob | Hotels | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 162 | 0 | 67 | 97 |  | Planning | Travel | Jeff | Transportation | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 154 | 0 | 89 | 366 |  | Implementation | Manager | Jeff | Ticket Sales | 2022-11-09 | 2023-11-30 |  |  | 277 | Yes | 118FS-90 edays | Yes | 89 | Green
No | No | 155 | 0 | 67 | 221 |  | Implementation | PR | Jeff | Promotional events | 2022-10-10 | 2023-05-11 |  |  | 154 | Yes | 118FS-120 edays | Yes | 67 | Green
No | No | 156 | 0 | 67 | 303 |  | Implementation | PR | Jeff | Radio advertising buys | 2022-10-10 | 2023-09-04 |  |  | 236 | No | 118FS-120 edays | Yes | 67 | Green
No | No | 157 | 0 | 67 | 303 |  | Implementation | PR | Jeff | TV advertising buys | 2022-10-10 | 2023-09-04 |  |  | 236 | No | 118FS-120 edays | Yes | 67 | Green
No | No | 158 | 0 | 147 | 424 |  | Implementation | PR/Band | Jeff | Promotional Interviews | 2023-01-30 | 2024-02-20 |  |  | 277 | Yes | 118FS-10 edays | Yes | 147 | Green
No | No | 16 | 0 | 141 | 153 |  | Go Live | Band | Bob | Copenhagen, Denmark | 2023-01-20 | 2023-02-06 |  |  | 12 | Yes |  | Yes | 141 | Green
No | No | 28 | 0 | 175 | 193 |  | Go Live | Band | Bob | Stockholm, Sweden | 2023-03-09 | 2023-04-03 |  |  | 18 | Yes | 118FS+30 edays | Yes | 175 | Green
No | No | 29 | 0 | 175 | 195 |  | Go Live | Band | Bob | Berlin, Germany | 2023-03-09 | 2023-04-05 |  |  | 20 | Yes | 118FS+30 edays | Yes | 175 | Green
No | No | 30 | 0 | 175 | 185 |  | Go Live | Band | Bob | Manchester, England | 2023-03-09 | 2023-03-22 |  |  | 10 | Yes | 118FS+30 edays | Yes | 175 | Green

## Raw Schedule
Last Update 07-06-2022 |  | Return to the table of contents
Task Mode | Critical | Summary | Task ID * | % Complete | Days Until Start + | Days Until Finish + | Days Since Completed + | Hub + | Work Stream + | Project Manager * | Task Name | Start | Finish | Actual Start | Actual Finish | Duration | Key Deliverable + | Predecessors | Active | Summary2 | RAG +
Manually Scheduled | No | Yes | 1 | 8% | 0 days | 0 days |  |  | All | Jeff,Bob,Sam | Main Event Project Schedule | 4416600% | 4416600% | 4416600% | NA | 0 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 140 | 24% | -178 days | -177 days |  |  | All | Jeff,Bob,Sam | US Tour | 4416600% | 4456100% | 4416600% | NA | 285 days? | No |  | Yes | Yes | -178 days
Auto Scheduled | No | Yes | 2 | 40% | 0 days | 0 days |  |  | All | Jeff,Bob,Sam | US Tour Planning 2021 | 4416600% | 4456100% | 4416600% | NA | 285 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | Yes | Yes | 8 | 99% | -1 day | 0 days |  | Planning | Creative | Sam | Merchandising | 4423500% | 4437200% | 4423500% | NA | 101 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 9 | 100% | -369 days | -268 days | 268 | Planning | Creative | Sam | Promotional Artwork | 4423500% | 4437200% | 4423500% | 4437200% | 101 days | No | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | No | 44 | 100% | -314 days | -288 days | 288 | Planning | Manager | Sam | Design Approvals | 4431200% | 4434400% | 4431200% | 4434400% | 26 days | Yes | 22 | Yes | No | -314 days
Auto Scheduled | No | No | 43 | 100% | -369 days | -314 days | 314 | Planning | Vendor | Sam | Proof Design | 4423500% | 4430900% | 4423500% | 4430900% | 55 days | No | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | Yes | 11 | 0% | -1 day | 0 days |  | Implementation | Finance and Accounting | Jeff | Finance and Accounting | 4416600% | 4456100% | NA | NA | 285 days? | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 46 | 0% | -418 days | -133 days |  | Implementation | Finance and Accounting | Jeff | Payroll | 4416600% | 4456100% | NA | NA | 285 days | Yes |  | Yes | No | -418 days
Auto Scheduled | No | No | 45 | 0% | -418 days | -133 days |  | Implementation | Finance and Accounting | Jeff | Taxes | 4416600% | 4456100% | NA | NA | 285 days? | Yes |  | Yes | No | -418 days
Auto Scheduled | No | No | 48 | 0% | -418 days | -133 days |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 4416600% | 4456100% | NA | NA | 285 days? | No |  | Yes | No | -418 days
Auto Scheduled | No | No | 47 | 0% | -418 days | -133 days |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 4416600% | 4456100% | NA | NA | 285 days? | No |  | Yes | No | -418 days
Auto Scheduled | No | Yes | 6 | 100% | -1 day | 0 days |  | Planning | Human Resources | Bob | Crew | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 39 | 100% | -369 days | -339 days | 339 | Planning | Human Resources | Bob | Hiring | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | Yes | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | No | 38 | 100% | -369 days | -339 days | 339 | Planning | Human Resources | Bob | Training | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | No | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | Yes | Yes | 7 | 99% | -1 day | 0 days |  | Planning | Logistics | Sam | Equipment | 4423500% | 4435700% | 4423500% | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 41 | 100% | -369 days | -279 days | 279 | Planning | Logistics | Sam | Rentals | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | No | 42 | 100% | -369 days | -279 days | 279 | Planning | Logistics | Sam | Purchasing | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | No | 40 | 100% | -369 days | -339 days | 339 | Planning | Logistics | Sam | Shipping - Venue to Venue | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | Yes | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | Yes | 4 | 100% | -1 day | 0 days |  | Planning | Manager | Bob | Venues | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 36 | 100% | -369 days | -279 days | 279 | Planning | Manager | Bob | Contracts | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | No | No | 37 | 100% | -369 days | -279 days | 279 | Planning | Manager | Bob | Ryders | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -369 days
Auto Scheduled | Yes | Yes | 5 | 99% | -1 day | 0 days |  | Planning | Manager | Bob | Tour Route | 4428000% | 4436200% | 4428000% | NA | 60 days | No | 37FS-120 days | Yes | Yes | -1 day
Auto Scheduled | No | No | 33 | 100% | -336 days | -276 days | 276 | Planning | Manager | Bob | Vehice Leasing | 4428000% | 4436200% | 4428000% | 4436200% | 60 days | No | 37FS-120 edays | Yes | No | -336 days
Auto Scheduled | No | No | 35 | 100% | -336 days | -306 days | 306 | Planning | Manager | Bob | Licensing and Insurance | 4428000% | 4432000% | 4428000% | 4432000% | 30 days | No | 37FS-120 edays | Yes | No | -336 days
Auto Scheduled | No | Yes | 3 | 75% | -1 day | 0 days |  | Planning | Travel | Jeff | Booking | 4423700% | 4427800% | 4423700% | NA | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 32 | 50% | -367 days | -337 days |  | Planning | Travel | Jeff | Hotels | 4423700% | 4427800% | 4423700% | NA | 30 days | Yes | 37FS-120 days | Yes | No | -367 days
Auto Scheduled | No | No | 31 | 100% | -367 days | -337 days | 337 | Planning | Travel | Jeff | Transportation | 4423700% | 4427800% | 4423700% | 4427800% | 30 days | Yes | 37FS-120 days | Yes | No | -367 days
Auto Scheduled | Yes | Yes | 12 | 0% | 0 days | 0 days |  |  | All | Jeff,Bob,Sam | US Pre Tour Events 2021 | 4416600% | 4452500% | NA | NA | 259 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | Yes | No | 49 | 0% | -418 days | -264 days |  | Planning | Band | Bob | Rehearsals | 4416600% | 4437800% | NA | NA | 154 days? | Yes | 37FS-240 days | Yes | No | -418 days
Auto Scheduled | No | No | 50 | 0% | -309 days | -159 days |  | Implementation | Manager | Bob | Ticket Sales | 4431700% | 4452500% | NA | NA | 150 days? | Yes |  | Yes | No | -309 days
Auto Scheduled | No | No | 51 | 0% | -418 days | -264 days |  | Implementation | PR | Bob | Promotional events | 4416600% | 4437800% | NA | NA | 154 days? | Yes |  | Yes | No | -418 days
Auto Scheduled | No | No | 56 | 0% | -395 days | -159 days |  | Implementation | PR | Bob | Radio advertising buys | 4419700% | 4452500% | NA | NA | 236 days? | No |  | Yes | No | -395 days
Auto Scheduled | No | No | 55 | 0% | -395 days | -159 days |  | Implementation | PR | Bob | TV advertising buys | 4419700% | 4452500% | NA | NA | 236 days? | No |  | Yes | No | -395 days
Auto Scheduled | No | No | 54 | 0% | -418 days | -159 days |  | Implementation | PR/Band | Bob | Promotional Interviews | 4416600% | 4452500% | NA | NA | 259 days? | Yes |  | Yes | No | -418 days
Auto Scheduled | Yes | Yes | 13 | 0% | 0 days | 0 days |  | Go Live | Band | Bob | US Tour Year 2021 | 4437900% | 4452500% | NA | NA | 105 days | No |  | Yes | Yes | 0 days
Auto Scheduled | Yes | No | 20 | 0% | -264 days | -249 days |  | Go Live | Band | Bob | New York, NY | 4437900% | 4439900% | NA | NA | 15 days | Yes |  | Yes | No | -264 days
Auto Scheduled | No | No | 19 | 0% | -247 days | -227 days |  | Go Live | Band | Bob | Philadelphia, PA | 4440400% | 4443100% | NA | NA | 20 days | Yes | 37FS+2 days | Yes | No | -247 days
Auto Scheduled | No | No | 18 | 0% | -225 days | -201 days |  | Go Live | Band | Bob | Washington, DC | 4443400% | 4446700% | NA | NA | 24 days | Yes | 38FS+2 days | Yes | No | -225 days
Auto Scheduled | No | No | 17 | 0% | -199 days | -189 days |  | Go Live | Band | Bob | New Orleans, LA | 4447000% | 4448300% | NA | NA | 10 days | Yes | 39FS+2 days | Yes | No | -199 days
Auto Scheduled | No | No | 22 | 0% | -184 days | -174 days |  | Go Live | Band | Bob | Austin, TX | 4449100% | 4450400% | NA | NA | 10 days | Yes | 40FS+5 days | Yes | No | -184 days
Auto Scheduled | No | No | 21 | 0% | -169 days | -159 days |  | Go Live | Band | Bob | Los Angeles, CA | 4451200% | 4452500% | NA | NA | 10 days | Yes | 41FS+5 days | Yes | No | -169 days
Auto Scheduled | No | Yes | 141 | 0% | -178 days | -177 days |  |  | All | Jeff,Bob,Sam | Canadian Tour | 4446900% | 4496500% | NA | NA | 355 days? | No |  | Yes | Yes | -178 days
Auto Scheduled | No | Yes | 90 | 0% | 0 days | 0 days |  |  | All | Jeff,Bob,Sam | Canadian Tour Planning 2022 | 4446900% | 4492600% | NA | NA | 327 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 107 | 0% | -1 day | 0 days |  | Planning | Creative | Jeff | Merchandising | 4446900% | 4459400% | NA | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 108 | 0% | -200 days | -110 days |  | Planning | Creative | Jeff | Promotional Artwork | 4446900% | 4459400% | NA | NA | 90 days | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 110 | 0% | -200 days | -186 days |  | Planning | Manager | Bob | Design Approvals | 4446900% | 4448800% | NA | NA | 14 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 109 | 0% | -200 days | -170 days |  | Planning | Vendor | Sam | Proof Design | 4446900% | 4451000% | NA | NA | 30 days | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | Yes | 111 | 0% | -1 day | 0 days |  | Implementation | Finance and Accounting | Jeff | Finance and Accounting | 4453100% | 4492600% | NA | NA | 283 days? | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 112 | 0% | -156 days | 127 days |  | Implementation | Finance and Accounting | Jeff | Payroll | 4453100% | 4492600% | NA | NA | 283 days? | Yes |  | Yes | No | -156 days
Auto Scheduled | No | No | 113 | 0% | -156 days | 127 days |  | Implementation | Finance and Accounting | Jeff | Taxes | 4453100% | 4492600% | NA | NA | 283 days? | Yes |  | Yes | No | -156 days
Auto Scheduled | No | No | 114 | 0% | -156 days | 127 days |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 4453100% | 4492600% | NA | NA | 283 days? | No |  | Yes | No | -156 days
Auto Scheduled | No | No | 115 | 0% | -156 days | 127 days |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 4453100% | 4492600% | NA | NA | 283 days? | No |  | Yes | No | -156 days
Auto Scheduled | No | Yes | 100 | 0% | -1 day | 0 days |  | Planning | Human Resources | Bob | Crew | 4446900% | 4451000% | NA | NA | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 101 | 0% | -200 days | -170 days |  | Planning | Human Resources | Bob | Hiring | 4446900% | 4451000% | NA | NA | 30 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 102 | 0% | -200 days | -170 days |  | Planning | Human Resources | Bob | Training | 4446900% | 4451000% | NA | NA | 30 days | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | Yes | 103 | 0% | -1 day | 0 days |  | Planning | Logistics | Bob | Equipment | 4446900% | 4459400% | NA | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 104 | 0% | -200 days | -110 days |  | Planning | Logistics | Bob | Rentals | 4446900% | 4459400% | NA | NA | 90 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 105 | 0% | -200 days | -110 days |  | Planning | Logistics | Bob | Purchasing | 4446900% | 4459400% | NA | NA | 90 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 106 | 0% | -200 days | -170 days |  | Planning | Logistics | Bob | Shipping - Venue to Venue | 4446900% | 4451000% | NA | NA | 30 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | Yes | 94 | 0% | -1 day | 0 days |  | Planning | Manager | Bob | Venues | 4446900% | 4459400% | NA | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 95 | 0% | -200 days | -110 days |  | Planning | Manager | Bob | Contracts | 4446900% | 4459400% | NA | NA | 90 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 96 | 0% | -200 days | -110 days |  | Planning | Manager | Bob | Ryders | 4446900% | 4459400% | NA | NA | 90 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | Yes | 97 | 0% | -1 day | 0 days |  | Planning | Manager | Bob | Tour Route | 4446900% | 4455200% | NA | NA | 60 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 98 | 0% | -200 days | -140 days |  | Planning | Manager | Bob | Vehice Leasing | 4446900% | 4455200% | NA | NA | 60 days | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 99 | 0% | -200 days | -170 days |  | Planning | Manager | Bob | Licensing and Insurance | 4446900% | 4451000% | NA | NA | 30 days | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | Yes | 91 | 0% | -1 day | 0 days |  | Planning | Travel | Jeff | Booking | 4446900% | 4451000% | NA | NA | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 92 | 0% | -200 days | -170 days |  | Planning | Travel | Jeff | Hotels | 4446900% | 4451000% | NA | NA | 30 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 93 | 0% | -200 days | -170 days |  | Planning | Travel | Jeff | Transportation | 4446900% | 4451000% | NA | NA | 30 days | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | Yes | 133 | 0% | 0 days | 0 days |  |  | All | Bob,Jeff,Sam | Canadian Pre Tour Events 2022 | 4446900% | 4496500% | NA | NA | 355 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 134 | 0% | -354 days | -200 days |  | Planning | Band | Bob | Rehearsals | 4425600% | 4446800% | NA | NA | 154 days? | Yes | 78FS-240 days | No | No | -354 days
Auto Scheduled | No | No | 135 | 0% | -178 days | 99 days |  | Implementation | Manager | Jeff | Ticket Sales | 4450100% | 4488700% | NA | NA | 277 days? | Yes | 78FS-90 edays | Yes | No | -178 days
Auto Scheduled | No | No | 136 | 0% | -200 days | -46 days |  | Implementation | PR | Sam | Promotional events | 4446900% | 4468400% | NA | NA | 154 days? | Yes | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 137 | 0% | -200 days | 36 days |  | Implementation | PR | Sam | Radio advertising buys | 4446900% | 4479800% | NA | NA | 236 days? | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 138 | 0% | -200 days | 36 days |  | Implementation | PR | Sam | TV advertising buys | 4446900% | 4479800% | NA | NA | 236 days? | No | 78FS-120 edays | Yes | No | -200 days
Auto Scheduled | No | No | 139 | 0% | -122 days | 155 days |  | Implementation | PR/Band | Bob | Promotional Interviews | 4457900% | 4496500% | NA | NA | 277 days? | Yes | 78FS-10 edays | Yes | No | -122 days
Auto Scheduled | No | Yes | 146 | 0% | 0 days | 0 days |  | Go Live | Band | Bob | Canadian Tour year 2022 | 4457500% | 4476400% | NA | NA | 136 days | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 147 | 0% | -124 days | -114 days |  | Go Live | Band | Bob | Vancouver, BC | 4457500% | 4458800% | NA | NA | 10 days | Yes |  | Yes | No | -124 days
Auto Scheduled | No | No | 148 | 0% | -93 days | -81 days |  | Go Live | Band | Bob | Ottawa, ON | 4462000% | 4463500% | NA | NA | 12 days | Yes | 78FS+30 edays | Yes | No | -93 days
Auto Scheduled | No | No | 149 | 0% | -59 days | -49 days |  | Go Live | Band | Bob | Perth, ON | 4466600% | 4467900% | NA | NA | 10 days | Yes | 79FS+30 edays | Yes | No | -59 days
Auto Scheduled | No | No | 150 | 0% | -28 days | -13 days |  | Go Live | Band | Bob | Montreal, QB | 4471100% | 4472900% | NA | NA | 15 days | Yes | 80FS+30 edays | Yes | No | -28 days
Auto Scheduled | No | No | 151 | 0% | -3 days | 12 days |  | Go Live | Band | Bob | Quebec, QB | 4474600% | 4476400% | NA | NA | 15 days | Yes | 81FS+15 edays | Yes | No | -3 days
Auto Scheduled | Yes | Yes | 145 | 0% | -178 days | -177 days |  | Go Live | Band | Bob | European Tour Year 2023 | 4484400% | 4558000% | NA | NA | 527 days? | Yes |  | Yes | Yes | -178 days
Auto Scheduled | Yes | Yes | 159 | 0% | 0 days | 0 days |  |  | All | Jeff,Bob,Sam | European Tour Planning 2023 | 4484400% | 4558000% | NA | NA | 527 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 176 | 0% | -1 day | 0 days |  | Planning | Creative | Jeff | Merchandising | 4484400% | 4496700% | NA | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 177 | 0% | 67 days | 157 days |  | Planning | Creative | Sam | Promotional Artwork | 4484400% | 4496700% | NA | NA | 90 days | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 179 | 0% | 67 days | 81 days |  | Planning | Manager | Bob | Design Approvals | 4484400% | 4486100% | NA | NA | 14 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 178 | 0% | 67 days | 97 days |  | Planning | Vendor | Jeff | Proof Design | 4484400% | 4488300% | NA | NA | 30 days | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | Yes | Yes | 180 | 0% | -1 day | 0 days |  | Implementation | Finance and Accounting | Sam | Finance and Accounting | 4489600% | 4558000% | NA | NA | 489 days? | No |  | Yes | Yes | -1 day
Manually Scheduled | Yes | No | 181 | 0% | 312 days | 594 days |  | Implementation | Finance and Accounting | Bob | Payroll | 4518700% | 4558000% | NA | NA | 282 days | Yes | 121FS+30 edays | Yes | No | 312 days
Auto Scheduled | No | No | 182 | 0% | 105 days | 387 days |  | Implementation | Finance and Accounting | Jeff | Taxes | 4489600% | 4529100% | NA | NA | 282 days? | Yes |  | Yes | No | 105 days
Auto Scheduled | No | No | 183 | 0% | 105 days | 387 days |  | Implementation | Finance and Accounting | Sam | Accounts recivable | 4489600% | 4529100% | NA | NA | 282 days? | No |  | Yes | No | 105 days
Auto Scheduled | No | No | 184 | 0% | 105 days | 387 days |  | Implementation | Finance and Accounting | Bob | Accounts Payable | 4489600% | 4529100% | NA | NA | 282 days? | No |  | Yes | No | 105 days
Auto Scheduled | No | Yes | 169 | 0% | -1 day | 0 days |  | Planning | Human Resources | Jeff | Crew | 4484400% | 4488300% | NA | NA | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 170 | 0% | 67 days | 97 days |  | Planning | Human Resources | Sam | Hiring | 4484400% | 4488300% | NA | NA | 30 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 171 | 0% | 67 days | 97 days |  | Planning | Human Resources | Bob | Training | 4484400% | 4488300% | NA | NA | 30 days | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | Yes | 172 | 0% | -1 day | 0 days |  | Planning | Logistics | Jeff | Equipment | 4484400% | 4496700% | NA | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 173 | 0% | 67 days | 157 days |  | Planning | Logistics | Sam | Rentals | 4484400% | 4496700% | NA | NA | 90 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 174 | 0% | 67 days | 157 days |  | Planning | Logistics | Bob | Purchasing | 4484400% | 4496700% | NA | NA | 90 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 175 | 0% | 67 days | 97 days |  | Planning | Logistics | Jeff | Shipping - Venue to Venue | 4484400% | 4488300% | NA | NA | 30 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | Yes | 163 | 0% | -1 day | 0 days |  | Planning | Manager | Sam | Venues | 4484400% | 4496700% | NA | NA | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 164 | 0% | 67 days | 157 days |  | Planning | Manager | Bob | Contracts | 4484400% | 4496700% | NA | NA | 90 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 165 | 0% | 67 days | 157 days |  | Planning | Manager | Jeff | Ryders | 4484400% | 4496700% | NA | NA | 90 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | Yes | 166 | 0% | -1 day | 0 days |  | Planning | Manager | Sam | Tour Route | 4484400% | 4492500% | NA | NA | 60 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 167 | 0% | 67 days | 127 days |  | Planning | Manager | Bob | Vehice Leasing | 4484400% | 4492500% | NA | NA | 60 days | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 168 | 0% | 67 days | 97 days |  | Planning | Manager | Jeff | Licensing and Insurance | 4484400% | 4488300% | NA | NA | 30 days | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | Yes | 160 | 0% | -1 day | 0 days |  | Planning | Travel | Sam | Booking | 4484400% | 4488300% | NA | NA | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 161 | 0% | 67 days | 97 days |  | Planning | Travel | Bob | Hotels | 4484400% | 4488300% | NA | NA | 30 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 162 | 0% | 67 days | 97 days |  | Planning | Travel | Jeff | Transportation | 4484400% | 4488300% | NA | NA | 30 days | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | Yes | 152 | 0% | 0 days | 0 days |  |  | All | Jeff,Bob,Sam | European Pre Tour Events 2023 | 4484400% | 4534200% | NA | NA | 357 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 153 | 0% | -354 days | -200 days |  | Planning | Band | Bob | Rehearsals | 4425600% | 4446800% | NA | NA | 154 days? | Yes | 78FS-240 days | No | No | -354 days
Auto Scheduled | No | No | 154 | 0% | 89 days | 366 days |  | Implementation | Manager | Jeff | Ticket Sales | 4487400% | 4526000% | NA | NA | 277 days? | Yes | 118FS-90 edays | Yes | No | 89 days
Auto Scheduled | No | No | 155 | 0% | 67 days | 221 days |  | Implementation | PR | Jeff | Promotional events | 4484400% | 4505700% | NA | NA | 154 days? | Yes | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 156 | 0% | 67 days | 303 days |  | Implementation | PR | Jeff | Radio advertising buys | 4484400% | 4517300% | NA | NA | 236 days? | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 157 | 0% | 67 days | 303 days |  | Implementation | PR | Jeff | TV advertising buys | 4484400% | 4517300% | NA | NA | 236 days? | No | 118FS-120 edays | Yes | No | 67 days
Auto Scheduled | No | No | 158 | 0% | 147 days | 424 days |  | Implementation | PR/Band | Jeff | Promotional Interviews | 4495600% | 4534200% | NA | NA | 277 days? | Yes | 118FS-10 edays | Yes | No | 147 days
Auto Scheduled | No | Yes | 15 | 0% | 0 days | 0 days |  | Go Live | Band | Bob | European Tour Year 2023 | 4494600% | 4502100% | NA | NA | 54 days | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 16 | 0% | 141 days | 153 days |  | Go Live | Band | Bob | Copenhagen, Denmark | 4494600% | 4496300% | NA | NA | 12 days | Yes |  | Yes | No | 141 days
Auto Scheduled | No | No | 28 | 0% | 175 days | 193 days |  | Go Live | Band | Bob | Stockholm, Sweden | 4499400% | 4501900% | NA | NA | 18 days | Yes | 118FS+30 edays | Yes | No | 175 days
Auto Scheduled | No | No | 29 | 0% | 175 days | 195 days |  | Go Live | Band | Bob | Berlin, Germany | 4499400% | 4502100% | NA | NA | 20 days | Yes | 118FS+30 edays | Yes | No | 175 days
Auto Scheduled | No | No | 30 | 0% | 175 days | 185 days |  | Go Live | Band | Bob | Manchester, England | 4499400% | 4500700% | NA | NA | 10 days | Yes | 118FS+30 edays | Yes | No | 175 days

## File Info
Last Update 07-06-2022 |  | Return to the table of contents
Name | Extension | Date accessed | Date modified | Date created | Folder Path
Documentation - project status reporting.docx | .docx | 2022-07-06 13:41 | 2022-07-06 13:41 | 2022-07-06 12:26
Milestone Status Report July 2022.xlsm | .xlsm | 2022-07-06 12:57 | 2022-07-06 12:57 | 2022-07-06 11:17
Project Schedule July 2022.mpp | .mpp | 2022-07-06 13:46 | 2022-07-06 13:28 | 2022-07-06 11:53
RAG Report July 2022.xlsx | .xlsx | 2022-07-06 13:32 | 2022-07-06 13:32 | 2022-07-06 11:16
~$cumentation - project status reporting.docx | .docx | 2022-07-06 13:34 | 2022-07-06 12:26 | 2022-07-06 12:26
~WRL0838.tmp | .tmp | 2022-07-06 13:49 | 2022-07-06 12:26 | 2022-07-06 12:26